## Sheet1
Step No | Checkpoints | Milestones
Issuance of LOA (Project Allocation) / LOI
1 |  | Issuance of LOA
2 |  | Tariff Adoption Approval
3 |  | Power Purchase Agreement
4 |  | Power Supply Agreement
Applied for connectivity (NSWS)
5 |  | Stage - I Connectivity Approval
6 |  | Stage - II Connectivity Approval
7 |  | Long Term Access (LTA)
8 |  | Power Evacuation Approval
9 |  | In principal / Scheme approval
10 |  | Evacuation Feasbility Approval
11 |  | Transmission Agreement
12 |  | Transmission Service Agreement
13 |  | Long Term Access (LTA) Agreement
14 |  | Wheeling & Banking Agreement
15 |  | Bay Extension approval
16 |  | Bay Allocation Approval
17 |  | Connection Agreement
Conn BG 1/2
18 |  | Interconnection Approval
19 |  | Transmission Line - Route Approval
20 |  | Section 68 Approval
21 |  | Section 164 Approval
22 |  | NHAI Crossing NoC
23 |  | Railway Crossing NoC
24 |  | Defence NoC
25 |  | Forest NoC for Transmission Line
26 |  | PTCC Approval /Inspection / Inspection waiver
27 |  | Right of Way for Transmission Line
28 |  | MCT / Transmission Line Sharing Agreement
29 |  | Soil classification approval for Transmisson Line & S/S
30 |  | CEA / CEIG drawing approval for Transmission Line
31 |  | CEA / CEIG drawing approval for Bay Extension
32 |  | License for working for HT line
33 |  | ABT Meter inspection & Calibration
34 |  | Line Clearance Certificate for Transmission Line
35 |  | SLDC / RLDC Communication Scheme Approval
36 |  | SCADA connectivity approval
37 |  | Temporary Power Connection from Utility
38 |  | HT Service connection agreement
39 |  | Power Connection from Utility
Conn BG 3/4
40 |  | Nodal Agency Registration
41 |  | No-objection certificate from energy department
42 |  | NOC from Gram Panchayat for Development of Project
43 |  | CLRA Registration - For Construction
44 |  | Labour Licences - For Construction
45 |  | Building plan approval from DTCP
46 |  | Factory Plan approval & Registration
47 |  | Factory License
48 |  | BOCW Registration & Cess
49 |  | Geology and Mining
50 |  | NoC - Civil Aviation Department
51 |  | Fire-No Objection Certificate - Construction phase
52 |  | Industrial Entrepreneur's Memo.(IEM)- Part-I (Before Const.)
53 |  | CLRA Registration - For Operation
54 |  | Environmental Clearance from MoEF - Complaince / Exemption Documents
55 |  | Consent to Establish (CTE)
56 |  | Consent to Operate (CTO)
57 |  | Water supply from Irrigation Dept. for Operation
58 |  | Water supply from Ground Water Dept. for Operation
59 |  | MNRE Approval for Excise/Custom Exemption
60 |  | Nodal Agency Letter for MNRE Exemption
61 |  | MNRE Reconcillation certificate
62 |  | VAT exemption / refund
63 |  | CEA / CEIG drawing approval for Project
64 |  | Industrial Entrepreneur's Memo.-Part-II(IEM)-II
65 |  | Periodic inspections of CEIG
66 |  | Road Entry Permit for Contractor to bring Material to site
67 |  | Authorization for handling solid waste
68 |  | Fire-No Objection Certificate - Operational phase
69 |  | Project Insurance - O&M
Commissioning
70 |  | Work Completion Certificate from Transco - Project
71 |  | Work Completion Certificate from Transco - Trans. Line
72 |  | Work Completion Certificate from Transco - Bay Exten.
73 |  | Work Completion Certificate from Discom
74 |  | Meter Sealing Report
75 |  | Grid Synchronization Approval
76 |  | Safety Clearance Certificate by CEIG - Project
77 |  | Safety Clearance Certificate by CEIG - Transmission Line & Bay
78 |  | Syncronization Certificate
79 |  | Commissioning MoM
80 |  | Commissioning Certificate
81 |  | Commercial Operation Date (COD) Letter from DISCOM